## Project Planner
CONNOR BRIDLE PROJECT GANNT CHART
[6 empty] | 60 |  |  | Slack time | [5 empty] | Subsection |  |  |  |  | Full Section
ACTIVITY | Slack time | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Week
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
1: Project Plan | 1 | 10 | 1 | 6 | 1
1.1 Complete project plan form | 1 | 5 | 1 | 5
1.2 Complete GANNT chart | 4 | 3 | 4 | 3
2: Collecting literature | 1 | 10 | 1 | 8 | 1
2.1: Gain literature regarding nutrition | 1 | 10 | 1 | 6
2.2: Gain literature regarding UI Design | 4 | 7 | 4 | 4
2.3: Narrow down literature to only include the most relevant | 7 | 2 | 7 | 2
2.4 Highlight key information that could be cited in project report | 8 | 2 | 8 | 2
3: Produce series of UI Mockups | 9 | 3 | 9 | 2 | 1
3.1 Using literature develop UI mockup designs | 9 | 3 | 9 | 2
3.2 Create 3 options for user feedback | 10 | 2 | 10 | 1
4: Data collection regarding UI | 10 | 5 | 10 | 4 | 1
4.1 Develop questionaire regarding UI | 10 | 3 | 10 | 2
4.2 Present questionaire and designs to users | 12 | 2 | 12 | 1
4.3 Collate results from users | 13 | 2 | 13 | 1
5: Creation of rule set | 12 | 7 | 12 | 5 | 1
5.1 Establishing each rule required within system | 12 | 3 | 12 | 2
5.2 Implementing rule set programatically | 14 | 5 | 14 | 3
6: User interface implementation | 12 | 8 | 12 | 5 | 1
6.1 Consolodating user feedback | 12 | 2 | 12 | 1
6.2 Creation of final hand draw design | 13 | 2 | 13 | 1
6.3 Implementing design within Java | 14 | 6 | 14 | 3
7: Introduction of saved user profiles | 16 | 3 | 16 | 2 | 1
7.1 Introducing a create profile form | 16 | 2 | 16 | 1
7.2 Implement a way to save profile | 17 | 2 | 17 | 1
8: Testing software | 18 | 5 | 18 | 4 | 1
8.1 Unit testing | 18 | 3 | 18 | 2
8.2 Systematic testing | 20 | 3 | 20 | 2
9: Writing project report | 8 | 20 | 8 | 20 | 1